## TimeEstimation
Trinetra Wireless Pvt Ltd
| Time Estimation for customization points / features | Doc Ref : | 7.0:OFFSHORE/R 07/1.1
|  | Date: | 2018-09-24
Client
Date | 30-Jan-2019
S. No | Modules | Time Estimates (In Man Hours) | Summary | Milestone | Category | Remarks (If any)
1 | System Study |  | 36
| Technical Study | 12
| Proposal and SRS preparation | 24 |  | Y
2 | Project Planning |  | 4
| Project Plan | 4
Time estimation and Time line
3 | Design and Development |  | 44
| High Level Design | 16
| Detailed Design | 28
4 | Visual Prototype |  | 22 | Y
| Mobile – Android | 12
| Web | 10
5 | Coding
| Customization Features (Web) |  |  | 164
| Web service integration |  | 48
| MQTT/ SIGNAL R connection for two way communication | 24
| Web service integration for save location details (8 WS) | 16
| Web service integration for save call record (4 WS) | 8
| Voice / Chat communication management |  | 36
| Design and Development | 8
| Procedure implementation | 6
| Functionality implementation | 6
| Plugin implementation based on PoC | 10
| Privilege based enabling | 4
| Details export | 2
| Vehicle Management |  | 8
| Tweaks for mobile device management | 4
| Procedure implementation | 2
| Functionality implementation | 2
| Send Commands |  | 48
| 12 Commands process | 32
| Functionality implementation | 8
| Procedure implementation | 4
| Ws for command trigger and get response | 4
| For Driver management App |  | 24
| WS for route (2) | 4
| Ws for trip details (4) | 8
| WS for dropdowns (4) | 8
| WS for reports / like template visible with data | 4
| Customization Features (Mobile App) |  |  | 222
| Schedule |  | 18
| Screen design for schedule job | 6
| Functionality implementation | 8
| Web services integration | 4
| History |  | 18
| Screen design for schedule job | 6
| Functionality implementation | 8
| Web services integration | 4
| Fleet management |  | 18
| Screen design for schedule job | 6
| Functionality implementation | 8
| Web services integration | 4
| Two communication(Text) |  | 40
| Screen design for text message | 12
| Functionality implementation message send & receive | 20
| Web service integration | 8
| Two communication(Voice) |  | 58
| Screen design for voice call (request & receive) | 14
| Functionality implementation | 24
| Call recording | 12
| Web service integration | 8
| GPS tracking |  | 34
| Reporting interval functionality | 8
| Background services | 6
| Message framing | 12
| Web service integration | 8
| POC for two way communication for text message | 16 | 16
| POC for two way communication for voice call | 20 | 20
6 | Code Review | 4 | 4
7 | Testing & Implementation
| Mobile App |  | 56
| Completion of Test Cases | 12
| Testing & Bug closing | 30
| Test Report | 14
| Software |  | 54
| Completion of Test Cases | 8
| Testing & Bug closing | 44
| Test Report | 2
8 | User Manual |  | 0
9 | Project Release |  | 6
| Client's Server configuration | 2
Data Migration
| Mobile App deployment | 4
Server Migration
| User Training/ Client Visits / After Release Support Efforts (if Required) |  |  | Y
10 | Project Management |  | 4
Telecall
| Project Review (review done by PM) | 2
| Project briefing to testers, Team member clarifications, etc | 2
| Total time estimate | 616 | 616
| 5% Buffer | 30.8 | 30.8
| Total Hours | 646.8 | 646.8
| Total Man Days | 80.85 | 80.85
| Total man Months | 3.675 | 3.675
Plan A | Delivery Time line | 517.44 | 517.44 |  | 1 Software / 1 Mobile / 1 QA = 3 Resources
| Man days | 64.68 | 64.68
| Man weeks | 12.936 | 12.936
| Lead Time to start the project / process | 2 Weeks |  |  | Based on the current workload
Technology
ASP.NET 4.5 and Android
Technology – Mobile app
Android -5.0 to 8.0 & latest
Gray Area highlighted in Gray color
Assumption highlighted in Yellow Color
Mobile | Disclaimer:
1.1st we will do the PoC based on the result we proceed with the implementation. 2.Two way communication will be provided in the android mobile application. 3.Notification will be received when the job schedule is assigned to driver and respective task holders. 4.Text messages is only current day only. Filter is available to see the history of the chat. 5.We need to do POC for two communication(text & voice) in android android mobile application. 6.App need to run on foreground in mobile for better location accuracy. 7.For voice call the App need to run on foreground in mobile. 8.Mobile application user should ensure enough ram and memory space for application running.its completely depends upon the android mobile. 9.if any additional requirement in the standard modules will be taken as customization. 10.Efforts can derived based on requirement received, if any changes need this will be revised. 11.Android mobile users should white list the mobile application from the battery optimization apps and other background killing apps. 12.Offline data will not provided without internet user will not able to see any data regarding the application. 13.Android mobile will require strong Internet connection(3G/4G/WIFI). 14.User should enable all the permissions of the iWay mobile application. 15.Mobile Application will be available in below mentioned technologies.
Software | 1. For this requirement, TRINETRA will provide the FMS standard solution for fleet management tracking with the reporting mobile app device. 2. All the tracking data to be based on configuration done in vehicle management module like reporting intervals. 3. For voice and chat communication, TRINETRA using SIGNAL R concepts for real time communication between device and portal. This can achieve based on PoC result. 4. 6 commands are planned for querying the device and get the response as per scope. 5. Vehicle management module for manage all the tracking device configured and managed in the portal. 6. Apart from above key modules, major standard modules of fleet management solution to be provide as per the scope requirement. 7. Separate module for voice and chat communication are tracked in the portal. Histories to be loaded based on date selection and able to view by privilege users. 8. For FMS app which specially for drivers. Web services are planned for smooth transaction between app and portal through this approach. 9. TRINETRA plan to provide only which are the modules are applicable with android MDT supports. According to that, TRINETRA derive efforts for the scope and based on the consideration of PoC results with MDT devices. 10. Client will provide the android MDT device for the PoC and conclude the solution by TRINETRA one month before start the implementation. 11. As per requirement, TRINETRA derived the efforts with the above assumption. If any changes required, will consider as an enhancement and efforts will include with the current scope.
2) TRINETRA planned attendance module only in the portal side as per the requeset. Attendance details should shown in calendar with color details like Absent shown in red color / present shown in green color along with shift details. This module will comes under configuration.
3) For the notification mail, TRINETRA prepared the template for both mail and SMS & shared to client for confirmation. Based on confirmation, will implement the same in portal.
4) Attendance data is only available in the portal. There is no reports planned in this customization.
5) Apart from above mentioned / per scope, will consider as an enhancement if any new request / feedback comes.
5) Apart from above mentioned / per scope, will consider as an enhancement if any new request / feedback comes.
Assumptions made for arriving delivery timeline
Man days are planned for working days.
The release will be planned after the QA confirmations.
The plan drafted based on the 1 software, 1 mobile, and 1 QA resource