## Old (hidden)
S.No | Type | Description of the Findings | CORRECTION |  |  |  | ROOT CAUSE(S) OF THE PROBLEM |  | CORRECTIVE ACTION |  |  |  |  | EFFECTIVENESS REVIEW
|  |  | Action | Responsibility | EDC | ADC | Issue / Problem | Root Cause(s) | Action | Type | Responsibility | EDC | ADC | Corrective Action to Review | Reviewer | EDC | ADC | Comments / Status
Note on D11: NA for OS
Note on H11: NA for OI and OS
Note on J11: NA for OI and OS
Note on O11: NA for OI and OS

## CAR - Updated (hidden)
| ANGLER Technologies |  |  | Doc. Ref: | 6.4:MGMT/R 10/1.0
| CORRECTIVE ACTION REPORT |  |  | Rev.Date: | 14/08/09
SBU |  |  | Project code
Project Name |  |  | Prepared by
Executive Name |  |  | Prepared on
Team Members |  |  | Reviewed by
PM |  |  | Reviewed on
Step 1: Correction |  |  | TAT - 1 Day
Details |  |  | Correction |  |  |  | Correction - Effectivenss Review
S.No | Type | Description | Action | Responsibility | EDC | ADC | Correction Reviewed | Responsibility
Step 2 : Rootcause Analysis and Corrective Action |  |  | TAT - 2 Day
Rootcause Analysis |  |  | Corrective action | [5 empty] | Corrective action - Effectiveness Review
S.No | Issue | Root Cause Analysis | Action | Type | Responsibility | Corrective action Applicable SBU | EDC | ADC | Corrective action Reviewed | Responsibility
Step 3 : Impact Area & Impact Review |  |  | TAT - 1 Day
Impact Area - Responsibility - Executive | [6 empty] | Impact Review
S.No | Process Name | Document Template - Name (change if Applicable) | Document Ref number | Next steps for the Corrective action - Applicable SBU | Responsibility | DCR Approved - Date | Process Reviewed | Status of the next steps derived | Reviewed By | Remarks
Note on C13: 1.Complaint 2.Deviated KRA KRI 3.Long Pending POA 4.Internal Audit - Major NC 5. Internal Audit - Minor NC
Note on I12: Responsibility - CAR Reviewer
Note on I30: Responsibility - CAR Reviewer
Note on K21: Responsibility - CAR Reviewer

## Root cause - Stage 1
| ANGLER Technologies | [8 empty] | Doc. Ref: | 6.4:MGMT/R 15/1.1
| Rootcause Analysis Report | [8 empty] | Rev.Date: | 2017-10-31
SBU | Trinetra | Vertical | Deviation Type | RCA-Complaint | RCA Initiated Date | 31-Dec-2018 |  |  | Quality of RCA - Rootcause Analysis | 0
Project Name | RCPL |  | Deviation Severity | High - TAT 5 Days | Prepared by & Submitted on | 11-Jan-2019 |  |  | 1.a. RCA TAT -1/2 Point 2. Appropriate Rootcause which prevents the recurrence of the issue - 2 Points
PL & PM | Ranjith.n& shreeprakaash |  | CFT Applicability - Same or Other SBU / Vertical |  | Reviewed by & Review Date
Case Number (Generated in GTDHUB) |  |  | CFT Team details |  | RCA Review Count | 1st Review
Correction
S.No | Issue / Problem description (clearly state the Issue / Problem description) |  |  |  | Impact details (Impact about Client business, Internal BD impact & Technical SBU & Supporting SBU) |  |  |  | Correction Correction should indicate clearly about planned solution for Resolving the issue mentioned, considering the impact severity. - TAT - 1 Day |  |  | Responsibility | Correction - Effectiveness Review (Should verify the Correction Actual completion ) |  |  | Status with Remarks (Auditor approval & comments for Correction)
1 | Project release deviation due to missouts |  |  |  | bugs raised after post release impact on product quality it leads to multiple releases |  |  |  | need to followup release checklist and proper QA approval |  |  | Gnanaprakash
Root cause Analysis
S.No | Issue / Problem description (clearly breakdown the issues one by one & mention it below to find the Root causes considering the impact) |  | Reason (Clearly state the reason for each issue) |  |  | Reason 1 : Task planning stuck & Not achive functionality implementation as per commited EDC |  | Reason 2 : Missouts in Unit Test validation |  | Reason 3 :Deviation in QA Confimation for bugs closures & approval |  | Reason 4 : Missouts the bug fix integration in release build |  | Reason 5 :File fomat renaming & Code Merging incorrectly in release build
[6 empty] | Root Cause Analysis guidelines : 1. While listing the possible causes (One should not comment on others suggestion / comment. List all the causes then do the Why, Why Analysis) 2. Each reason should have one Root cause 3. One deviation / Non conformance can have multiple Root causes |  | Root Cause Analysis guidelines : 1. While listing the possible causes (One should not comment on others suggestion / comment. List all the causes then do the Why, Why Analysis) 2. Each reason should have one Root cause 3. One deviation / Non conformance can have multiple Root causes |  | Root Cause Analysis guidelines : 1. While listing the possible causes (One should not comment on others suggestion / comment. List all the causes then do the Why, Why Analysis) 2. Each reason should have one Root cause 3. One deviation / Non conformance can have multiple Root causes |  | Root Cause Analysis guidelines : 1. While listing the possible causes (One should not comment on others suggestion / comment. List all the causes then do the Why, Why Analysis) 2. Each reason should have one Root cause 3. One deviation / Non conformance can have multiple Root causes |  | Root Cause Analysis guidelines : 1. While listing the possible causes (One should not comment on others suggestion / comment. List all the causes then do the Why, Why Analysis) 2. Each reason should have one Root cause 3. One deviation / Non conformance can have multiple Root causes |  | Status with Remarks (Auditors approval & Comments for each Rootcause seperately) (Mandatory)
1 | Project release deviation due to muliple releases |  | Reason 1 : Task planning stuck & Not achive functionality implementation as per commited EDC |  |  | 1 - Why-Why Analysis | Design & Functionality as per request and requirement | 1 - Why-Why Analysis | The functionality implementation can take more development time | 1 - Why-Why Analysis | Looping of testing releases | 1 - Why-Why Analysis | Engaged in other tasks once if the task completion | 1 - Why-Why Analysis | On the release day bug raised | CFT - Not Applicable
|  |  | Reason 2 : Missouts in Unit Test validation |  |  | 2 - Why-Why Analysis | Re implement the functionalities as per suggestion from team side & support for other team dependency | 2 - Why-Why Analysis | Not followup developer check list as planned | 2 - Why-Why Analysis | Misunderstanding in Bug scenarios capture | 2 - Why-Why Analysis | Bug fix takes time for repeated single single fixes and suggestions | 2 - Why-Why Analysis | Big fix support dependency lack on deadline & support person engagement with other tasks or fix them release points closures | Rootcause Quality -Meets Expectation
|  |  | Reason 3 :Deviation in QA Confimation for bugs closures & approval |  |  | 3 - Why-Why Analysis | SRS implemented based on product design but to meet reqiurement change the customization UI as per suggestion | 3 - Why-Why Analysis | Design functionalities updated or changed as per reqiurement and suggestion | 3 - Why-Why Analysis | Solutions finding for the bug fix | 3 - Why-Why Analysis | Not Aware the QA Test cases | 3 - Why-Why Analysis | Even minor issue fix takes short time but neck to neck pressure can leads final missouts
|  |  | Reason 4 : Missouts the bug fix integration in release build |  |  | 4 - Why-Why Analysis | to meet new ui and functionality changes not able to complete the task as per comitted EDC | 4 - Why-Why Analysis | short time for capture validation scenarios | 4 - Why-Why Analysis | Not Aware the QA Test cases | 4 - Why-Why Analysis | Not know the what deliverables to be released &lackness from team side | 4 - Why-Why Analysis | Except final application store release all the development release may occur the compatibility and release issues. Because application has protocols difference between development & release build
|  |  | Reason 5 :File fomat renaming & Code Merging incorrectly in release build |  |  | 5 - Why-Why Analysis | Handling multiple tasks(project/Non project) at the same time with same priority | 5 - Why-Why Analysis | The QA team raised followup for application with them EDC | 5 - Why-Why Analysis | Lack in communication with QA Team | 5 - Why-Why Analysis | Continue push pressure from team side in dead line | 5 - Why-Why Analysis | Users Not aware how to use the development releases
Root cause Root cause should be specified with clear description. Any one can read & understand without others help. | [5 empty] | Root cause 1 : |  | Root cause 2 : |  | Root cause 3: |  | Root cause 4: |  | Root cause 5:
Rating :
* - If Rootcause Rating is less than 1.25 then the Rootcause analysis to be re done
Note on E6: Vertical should be listed exactly as available in GTD Hub under POA category
Note on F8: Please refer the Dev. Sev. Rating sheet and enter the applicability
Note on F9: Select Appropriate CFT from CFT details sheet & Update relevant team members
Note on I6: Date Format : DD-MM-YYYY
Note on I7: First part of email ID & DD-MM-YYYY
Note on I8: First part of email ID & DD-MM-YYYY
Note on L6: Rating points - 1 to 5 should be given based on the below criteria
Note on R27: 1. RCA TAT - 1/2 point 2. Rootcause - 2 Point

## Corrective action - Stage 2
| ANGLER Technologies | [9 empty] | Doc. Ref: | 6.4:MGMT/R 15/1.1
| CORRECTIVE ACTION REPORT | [9 empty] | Rev.Date: | 2017-10-31
SBU | Trinetra | Vertical | 0 | Deviation Type | RCA-Complaint | RCA Initiated Date | 31-Dec-2018 |  |  | Quality of CAR - Corrective Action | 0 | Total Rating | 0
Project Name | RCPL |  |  | Deviation Severity | High - TAT 5 Days | Prepared by & Submitted on | 11-Jan-2019 |  |  | 1. CA TAT - 1/2 Point 2. Corrective Action which leads Process Changes / Document changes / Audit checklist updation / Training related requirements with Valid POAs - 2 Points
PL & PM | Ranjith.n& shreeprakaash |  |  | CFT Applicability - Same or Other SBU / Vertical | 0 | Reviewed by & Review Date | 0
Case Number (Generated in GTDHUB) | 0 |  |  | CFT Team details | 0 | Corrective action Review Count | 1st Review
Corrective Action
S.No | Root cause description Clearly state down the Root cause (Any body can read & understand without others help) |  |  | Corrective Action (Should Specify the Process Changes / Document changes / Audit checklist updation changes / Training related requirements) |  | Applicable SBUs | Corrective Action POA Description (Each POAs should be described clearly & Any body can read and understand POA without others help) | POA Type (Select the POA type from drop down) | EDC (Provide clear EDC for each POAs) | POA Category (Select the category from drop down) | Responsibility | Corrective Action Implementation Effectiveness Review (Should verify the Corrective action POA - Long Term & Short Term closure) | Status with Remarks (Mandatory)
1 | 0 | [11 empty] | CFT - Not Applicable
CA Quality -Meets Expectation
2 | 0 | [11 empty] | CA Quality -Meets Expectation
3 | 0 | [11 empty] | CA Quality -Meets Expectation
4 | 0
5 | 0
Rating
* - If CA Rating is less than 1.25 then the corrective action analysis to be re done
RCA - PPT
Highly deviated | RCA Initiated Date | Root cause analysed (Yes / No) | RCA ER completed |  | Corrective Action taken (Yes / No) | CA ER completed |  | POAs updated in GTD Hub (Yes / No) | POAs updated in MAP (If Applicable) | Responsibility | Open CA POAs with count | EDC | Revised EDC
|  |  | Yes / No | Quality of RCA rating |  | Yes / No | Quality of CA rating
RCA-Complaint | 31-Dec-2018 | No | Yes | 0 | Yes | Yes | 0 | Yes
S. No | Highly deviated |  |  |  |  | Root cause
1 | Project release deviation due to missouts |  |  |  |  | 0
2 | 0 |  |  |  |  | 0
3 | 0 |  |  |  |  | 0
4 | 0 |  |  |  |  | 0
5 | 0 |  |  |  |  | 0
S. No | Root cause description |  |  | Corrective Action |  |  | Corrective Action POA Description
1 | 0 |  |  | 0 |  |  | 0
0
0
0
0
S. No | Root cause description |  |  | Corrective Action |  |  | Corrective Action POA Description
2 | 0 |  |  | 0 |  |  | 0
0
0
0
0
S. No | Root cause description |  |  | Corrective Action |  |  | Corrective Action POA Description
3 | 0 |  |  | 0 |  |  | 0
0
0
0
0
S. No | Root cause description |  |  | Corrective Action |  |  | Corrective Action POA Description
4 | 0 |  |  | 0 |  |  | 0
0
0
0
0
S. No | Root cause description |  |  | Corrective Action |  |  | Corrective Action POA Description
5 | 0 |  |  | 0 |  |  | 0
0
0
0
0
Note on C13: Formula Driven
Note on C18: Formula Driven
Note on C23: Formula Driven
Note on C28: Formula Driven
Note on C33: Formula Driven
Note on F8: Please refer the Dev. Sev. Rating sheet and enter the applicability
Note on F9: Select Appropriate CFT from CFT details sheet & Update relevant team members
Note on K12: EDC Format - DD-MM-YYYY Eg: 10-11-2017
Note on L6: Rating points - 1 to 5 should be given based on the below criteria
Note on M6: Formula Driven
Note on N38: CA TAT - 1/2 point Corrective Action - 2 point
Note on O6: Formula Driven
Note on O38: CA TAT - 1/2 point Corrective Action - 2 point

## Dev.Sev.rating
ANGLER Technologies
Deviation -Severity
High Deviation Severity
S.No | Deviation Category | Deviation severity | TAT for High / Medium Severity deviation | CFT Applicability - Same SBU | CFT Applicability - Other SBU
1 | Complaints - External & Internal | Customer centricity related RCA (Internal & External) should be treated as High Severity deviation | TAT - High Severity deviation - 5 Days a. Correction - 1 Day b. Rootcause - 2 Days c.RCA Effectiveness Review - within 1/2 Day d. Corrective action - 1 Day e. CA Effectiveness Review -within 1/2 Day TAT - Medium Severity deviation - 4 Days a. Correction - 1 Day b. Deriving Rootcause & Effectiveness Review - 2 Days c. Corrective action & Effectiveness Review - 1 Day Note: the above TAT is the outer max limit, its always expected to close the RCA at the earliest to ensure client satisfaction, achieve KRI/Goals | Yes | Yes
2 | MAP - Metric completion - Low Achievement % (Less than 25%) |  |  | Yes | No
3 | Core KRI - Low Achievement % ( Below 60%) |  |  | Yes | No
4 | SBU / Product Audit - Repeated Major NCs (Occurance more than 2 times) |  |  | Yes | No
5 | Client Feedback - Low Achievement % ( Below 70%) -- All Applicable Client Feedbacks |  |  | Yes | No
6 | Preventive Action for any CAT - A Client (Forecast / Escalation - The deviation can forecast in advance & take necessary CFT inputs /guidance to prevent the deviation) |  |  | Yes | Yes
7 | Risk Areas & Mitigation plan matrix need to be updated in Quality Manual whenever & wherever received Customer Complaints (New / Exiting / Modification required) received |  |  | No | No
8 | External Audit |  |  | Yes | Yes