## TimeEstimation
Trinetra Wireless Pvt Ltd
| Time Estimation for customization points / features | Doc Ref : | 7.0:OFFSHORE/R 07/1.1
|  | Date: | 2018-09-24
Client | AVL
Date | 31-Jan-2019
S. No | Modules | Time Estimates (In Man Hours) | Summary | Milestone | Category | Remarks (If any)
1 | System Study |  | 48
| Technical Study | 16
| Proposal and SRS preparation | 32 |  | Y
2 | Project Planning |  | 6
| Project Plan | 6
Time estimation and Time line
3 | Design and Development |  | 56
| High Level Design | 24
| Detailed Design | 32
4 | Visual Prototype |  | 48 | Y
| Mobile – Android | 24
| Web | 24
5 | Coding
| Customization Features (Web) |  |  | 1208
| Web based graphical user interface (GUI) for all the business functionality which would comply with major web browsers like Internet Explorer, Mozilla. , LBS, GPSGIS, User info, Biometric Solution etc. | 12 | 12
| Capability of Integration with third-party authentication devices. | 32 | 32
| The system needs to be capable of intimating the concerned “Tehsildar” through SMS as well as outbound calls in case of any land related dispute calls from the citizens | 16 | 16
| Fuel Card and Driver Id card transaction summary |  | 18
| Page design | 8
| Database design | 6
| Table design | 4
Incoming calls at the ERC would be taken by Communication officers, calls for services shall be transferred to respective desks and actionable calls would be forwarded to Dispatch Officers and Special Dispatch Officers (in case of high importance calls). Based on the call assessment done through system, Dispatch Officer (DO) shall dispatch the ERV to incident site
| Voice / Chat communication management |  | 72
| Design and Development | 16
| Procedure implementation | 12
| Functionality implementation | 12
| Plugin implementation based on PoC | 20
| Privilege based enabling | 8
| Details export | 4
| Vehicle Management |  | 16
| Tweaks for mobile device management | 8
| Procedure implementation | 4
| Functionality implementation | 4
| Send Commands |  | 48
| 12 Commands process | 32
| Functionality implementation | 8
| Procedure implementation | 4
| Ws for command trigger and get response | 4
| Web service integration |  | 48
| MQTT/ SIGNAL R connection for two way communication | 24
| Web service integration for save location details (8 WS) | 16
| Web service integration for save call record (4 WS) | 8
| Create call Record |  | 126
| Design and Development includes validation | 24
| Functionality Implementation (NEW, EDIT, DELETE & VIEW) | 12
| Export Functionality in (PDF, XLS & DOC) | 16
| Others call record Add Provision in Panel | 16
| 1. The job status of the vehicle should be shown as given below. I. Inprogress – After the vehicle goes out of geozone – Automatic & Manual updates. II. Arrived – After the vehicle reaches the geozone(destination) the status changes to the status “arrived”. – Automatic & Manual updates. III. Completed – After the vehicle reaches the geozone and the door is opened the status is changed to completed. – Automatic and Manual updates. IV. Unassigned – After completed, if the vehicle goes out of the geozone then the unassigned status to be changed automatically. The manual updation also should be available. – Automatic & Manual updates. V. Cancelled – During the in progress job there may be possibility of cancellation and it should be done manually. – Manual updates. | 26
| 4. In Call log screen, multiple selection of locations(Start & destination) should be added. | 32
| Call Record Type Management |  | 36
| Design and Development | 8
| Functionality Implementation (NEW, EDIT, DELETE & VIEW) | 8
| Import Functionality with defined template | 12
| Export Functionality in (PDF, XLS & DOC) | 8
| Send SMS Tacking Unique ID |  | 20
| Template creation | 8
| Send SMS functionality | 12
| Call Log map page design |  | 60
| Voice log, Add Task, Route, Conference, GIS MAP: with enriched data and navigation keys. Even LBS will be used to see the location of caller | 12
| Map page design for call log tracking | 12
| Functionality implimentation | 8
| Export Functionality in (PDF, XLS & DOC) | 4
| The PFT close the case then the log will be update | 8
| Call record tracking | 16
| Dispatcher validates and prioritises the AbC’s at field level. The AbC’s, once classified and detailed by the COs, shall be passed by the system to one or more dispatchers | 18 | 18
| The CAD System shall display the information entered by the CO for AbCs. It would display the location as identified by the CO, ALI or address database but the dispatcher would also have the option of 'relocating' the AbC’s | 16 | 16
| Call history page |  | 48
| Listed all call log and status | 24
| Page design | 12
| Functionality implimentation | 8
| Export Functionality in (PDF, XLS & DOC) | 4
| ERV Status |  | 28
| The GIS shall display the assigned / unassigned ERVs using appropriate and intuitive graphical symbols | 12
| Unit shall report departure for, arrival at and, departure from a location and closure during incident handling | 4
| Vehicle beacon colour shall change automatically with their change in status, i.e. dispatch, arrival at scene, availability etc. | 4
| The entire movement of the vehicle would be time stamped and monitored by the Dispatcher | 4
| The Dispatcher shall be able to lock vehicle on map for continuous tracking | 4
| Communication between Dispatcher and ERV |  | 38
| Staff shall include: Call details sent from dispatcher via text to PFT device of ERV staff. Action taken receipt received by dispatcher. Action taken receipt not received by dispatcher. In that case, dispatcher shall call the ERV staff | 14
| Transmit the location and direction of the vehicle to the CAD system. Field unit shall not be able to switch off his GPS Tracking manually | 8
| The handheld PFTs shall have inbuilt camera with video. The PFTs shall have an audio recorder which shall be used, among other applications, for recording and transmitting the Action Taken Reports (ATR). It shall also be used to monitor attendance, vehicle utilization and other aspects of ERV management | 8
| Transmit and receive data through feature phones and Portable Field Tablet | 8
| Real time information of Patrol vehicles at any given point of time with location information over GIS-GPS | 24 | 24
| Dispatch of Police response vehicles based on least possible response time algorithm | 24 | 24
| Location tracking of caller through Maps | 12 | 12
| Geo-fencing of Police boundaries. Platform to integrate with other emergency services | 18 | 18
| Citizen Portal - Internet portal shall be used to provide feedback, history of the cases for registered users Citizen portal shall be used to display any kind of news, event and update which are published by Department o Citizen portal should also have the facility for Registration of Ambulances– Government and Private (Paid and Free Ambulance services) | 24 | 24
| Capture image & send |  | 22
| Functionality to capture the image while command receive | 12
| Functionality to send image to the server | 10
| System shall suggest the call takers |  | 36
| The system shall suggest the call takers and dispatcher the nearest and least response time ERV. | 18
| GIS coordinates of the person in distress (in case longitude/ latitude received by CRM) and emergency response vehicles would be displayed on the screen of the dispatch officer | 18
| Emergency response system |  | 24
| Page design | 12
| Functionality implimentation | 8
| Database design | 4
| Web service integration |  | 48
| MQTT/ SIGNAL R connection for two way communication | 24
| Web service integration for save location details (8 WS) | 16
| Web service integration for save call record (4 WS) | 8
| Voice / Chat communication management |  | 36
| Design and Development | 8
| Procedure implementation | 6
| Functionality implementation | 6
| Plugin implementation based on PoC | 10
| Privilege based enabling | 4
| Details export | 2
| Vehicle Management |  | 8
| Tweaks for mobile device management | 4
| Procedure implementation | 2
| Functionality implementation | 2
| Send Commands |  | 48
| 12 Commands process | 32
| Functionality implementation | 8
| Procedure implementation | 4
| Ws for command trigger and get response | 4
| For Driver management App |  | 24
| WS for route (2) | 4
| Ws for trip details (4) | 8
| WS for dropdowns (4) | 8
| WS for reports / like template visible with data | 4
| MAP related functionalities | 24 | 24
| Map Integration (Monitor & History) |  | 26
| Map Configuration | 8
| Map Tile Configuration | 4
| Marker Plotting with Infobubble | 6
| Polyline | 4
| Show Landmarks | 2
| Show Geozones | 2
| Landmark |  | 22
| Draw circle for landmarks | 6
| Getting Coordinates on map click | 2
| Search by address (Geocoding) | 12
| Marker Plotting with Infobubble | 2
| Geozone |  | 16
| Marker Plotting with Infobubble | 2
| Draw Polygon | 8
| Draw Rectangle | 6
| Routing |  | 26
| Route Draw | 10
| Getting the distance and time | 16
| Others |  | 82
| Multilingual Support | 8
| Clustering Support | 20
| Context Menu Support | 16
| Rectangular Zoom Support | 8
| Playback Feature | 30
| Services |  | 12
| Reverse Geocoding | 8
| Accessing Road Speed Limit through routing | 4
| Customization Features (Mobile App) – Location Identification |  |  | 222
| Schedule |  | 18
| Screen design for schedule job | 6
| Functionality implementation | 8
| Web services integration | 4
| History |  | 18
| Screen design for schedule job | 6
| Functionality implementation | 8
| Web services integration | 4
| Fleet management |  | 18
| Screen design for schedule job | 6
| Functionality implementation | 8
| Web services integration | 4
| Two communication(Text) |  | 40
| Screen design for text message | 12
| Functionality implementation message send & receive | 20
| Web service integration | 8
| Two communication(Voice) |  | 58
| Screen design for voice call (request & receive) | 14
| Functionality implementation | 24
| Call recording | 12
| Web service integration | 8
| GPS tracking |  | 34
| Reporting interval functionality | 8
| Background services | 6
| Message framing | 12
| Web service integration | 8
| POC for two way communication for text message | 16 | 16
| POC for two way communication for voice call | 20 | 20
6 | Code Review | 4 | 4
7 | Testing & Implementation
| Mobile App |  | 66
| Completion of Test Cases | 22
| Testing & Bug closing | 30
| Test Report | 14
| Software |  | 360
| Completion of Test Cases | 50
| Testing & Bug closing | 300
| Test Report | 10
8 | User Manual |  | 0
9 | Project Release |  | 42
| Client's Server configuration | 12
Data Migration
| Mobile App deployment | 6
| Server Migration | 24
| User Training/ Client Visits / After Release Support Efforts (if Required) |  |  | Y
10 | Project Management |  | 8
Telecall
| Project Review (review done by PM) | 4
| Project briefing to testers, Team member clarifications, etc | 4
| Total time estimate | 2068 | 2068
| 10% Buffer | 206.8 | 206.8
| Total Hours | 2274.8 | 2274.8
| Total Man Days | 284.35 | 284.35
| Total man Months | 12.925 | 12.925
Plan A | Delivery Time line | 1819.84 | 1819.84 |  | 1 Software / 1 Mobile / 1 QA = 3 Resources
| Man days | 227.48 | 227.48
| Man weeks | 45.496 | 45.496
| Lead Time to start the project / process | 2 Weeks |  |  | Based on the current workload
Technology
ASP.NET 4.5 and Android
Technology – Mobile app
Android -5.0 to 8.0 & latest
Gray Area highlighted in Gray color
Assumption highlighted in Yellow Color
Mobile | Disclaimer:
1.1st we will do the PoC based on the result we proceed with the implementation. 2.Two way communication will be provided in the android MDT device. 3.Notification will be received when the job schedule is assigned to driver and respective task holders. 4.Text messages is only current day only. Filter is available to see the history of the chat. 5.We need to do POC for two communication(text & voice) in android MDT. 6.App need to run on foreground in MDT for better location accuracy. 7.For voice call the App need to run on foreground in MDT. 8.Mobile application user should ensure enough ram and memory space for application running.its completely depends upon the android MDT. 9.if any additional requirement in the standard modules will be taken as customization. 10.Efforts can derived based on requirement received, if any changes need this will be revised. 11.Android MDT users should white list the mobile application from the battery optimization apps and other background killing apps. 12.Offline data will not provided without internet user will not able to see any data regarding the application. 13.Android MDT will require strong Internet connection(3G/4G/WIFI). 14.User should enable all the permissions of the iWay mobile application. 15.Mobile Application will be available in below mentioned technologies.
Software | 1. For this requirement, TRINETRA will provide the FMS standard solution for fleet management tracking with the reporting mobile app device. 2. All the tracking data to be based on configuration done in vehicle management module like reporting intervals. 3. For voice and chat communication, TRINETRA using SIGNAL R concepts for real time communication between device and portal. This can achieve based on PoC result. 4. 6 commands are planned for querying the device and get the response as per scope. 5. Vehicle management module for manage all the tracking device configured and managed in the portal. 6. Apart from above key modules, major standard modules of fleet management solution to be provide as per the scope requirement. 7. Separate module for voice and chat communication are tracked in the portal. Histories to be loaded based on date selection and able to view by privilege users. 8. For FMS app which specially for drivers. Web services are planned for smooth transaction between app and portal through this approach. 9. TRINETRA plan to provide only which are the modules are applicable with android MDT supports. According to that, TRINETRA derive efforts for the scope and based on the consideration of PoC results with MDT devices. 10. Client will provide the android MDT device for the PoC and conclude the solution by TRINETRA one month before start the implementation. 11. As per requirement, TRINETRA derived the efforts with the above assumption. If any changes required, will consider as an enhancement and efforts will include with the current scope. 12) Manage records & assignment planned as combined module, admin or privilege user can manage this module and assign to vehicle based on their plan. 13) Once planned the record to the respective vehicle, automatically assigned landmark / geozones to respective vehicle by schedule of command techniques since the geozone assignment works once it assigned to vehicle well OTA process. 14) record Types master planned for log the master data along with temperate if required. Order type list details should be shared by client. 15) ERP integration is not planned in this customization. If need, consider as an enhancement. 16) Route management planned with two modules. One is master from which user can create a route with different way points (min: 10). Other is assignment screen which user can assign the created route to vehicle before start the route. 17) Route assignment is not automatic process. Admin or privilege user can do manually in the portal as per their plan. 18) Route ETA included in this customization for view the current status. 19) Customized modules have default export option in 3 different type of format (pdf, xls and doc) 20) For SMS Notification, SMS Gateway will provide by client to integrate with TRINETRA. 21) For more than duration of 10 days data, data to be fetch from archive and shown the reports. Archive data reports to be planned only for standard reports. If additionally required, will consider as an enhancement. 22) Route Deviation logic define for finding alerts are available in email and SMS. 23) As per standard and defined duration in reports provided by TRINETRA for the effectiveness and best performances in generating report. 24) As per scope, TRINETRA will include the summary section in consolidated summary report. 25) All the alerts are to be triggered based on configure done by user in the portal. 26) Vehicle summary fine tune as per request includes. For best practices, data should be generate with minimum durations (like upto 2 weeks) or else performance will affects. TRINETRA suggest to use Fleet utilization summary standard report from report section. 27) Vehicle & Container (i.e head & tail) concepts to be manage in vehicle master screen through vehicle type in the portal. 28) Vehicle container mapping handle in separate assignment screen. Through this screen, assignment can be done by user manually. Based on assignment, history details and report details shown accordingly. 29) TRINETRA suggest to map the container based devices to separate fleet create & assign in the portal for easy references. 30) Admin can assign the container to vehicle through the assignment screen based on need. Assignment histories are available in assignment screen itself. 31) Apart from above, TRINETRA will consider as an enhancement if any modules to be add or fields to be include. 32) Latest version of map is v3.0. 33) Code level changes is required when compared to previous version v2.5.4 34) Need to do POC before implementation / modfication in the existing codes of TRINETRA application. 35) Grey area points are not supported in latest version V3.0. So we have to check the feasibility and alternate option is available to acheive the same. Drafted efforts based on assumption and It may vary once getting the solutions.
2) TRINETRA planned attendance module only in the portal side as per the requeset. Attendance details should shown in calendar with color details like Absent shown in red color / present shown in green color along with shift details. This module will comes under configuration.
3) For the notification mail, TRINETRA prepared the template for both mail and SMS & shared to client for confirmation. Based on confirmation, will implement the same in portal.
4) Attendance data is only available in the portal. There is no reports planned in this customization.
5) Apart from above mentioned / per scope, will consider as an enhancement if any new request / feedback comes.
5) Apart from above mentioned / per scope, will consider as an enhancement if any new request / feedback comes.
Assumptions made for arriving delivery timeline
Man days are planned for working days.
The release will be planned after the QA confirmations.
The plan drafted based on the 1 software, 1 mobile, and 1 QA resource